## Open
Defined Contribution Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Purchase of a 66 2/3% J&S Annuity for Member's retirement benefit or Transfer to Pension Plan for administering benefit. | Legal / BOT | Ed to seek options to purchase 66 2/3% J&S. Jeff to send info to Ed. Jeff had call with Snowden Lane Partners on 2/3/25 on options for member's J&S benefit. Exec. Cmte approved Athene for mbr's J&S benefit, working with Swonden Lane & member to complete applications | 2025-01-17
Retirement Guide | Legal / BOT | Legal has edits, Kenny has edit. One guide or separate guides, Julie last pass with final. Provided to Julie | 2025-01-17
Meeting Minutes Review of 3/7/23; 12/11/24; 1/29/25 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Valuation for PYE 12/31/24 | Acct'g / Fund Office / ISSI |  | 2025-01-17
Statements for PYE 12/31/24 | Fund Office |  | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase , Univest Bank & Trust, & Seacoast Bank. In communications with Key Bank | 2025-01-30
Defined Benefit Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Retirement Guide | Legal / BOT | Legal has edits, Kenny has edit. One guide or separate guides, Julie last pass with final. Provided to Julie | 2025-01-17
Determination of POA's request to direct deposit retirees benefit into their account and not members | Legal | Has been reviewed and Bill to send memo to Fund Office | 2025-01-17
Acceptance of DC Fund Account Balance for J&S Retirement Benefits | Legal / BOT / Actuary |  | 2025-01-17
Withdrawal calculation letter to Kaestle Enterprises for payment | Legal / Fund Office |  | 2025-01-30
Meeting Minutes Review of 2/16/23; 5/16/23; 11/26/24; 12/11/24; 1/29/25 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Verification Process - Ongoing Reinstatements | Fund Office |  | 2025-01-17
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Valuation for PYE 12/31/24 | Fund Office / Actuary | Data Request received from Ben, sent to ISSI for needed data. ISSI in process of sending to Ben | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase , Univest Bank & Trust, & Seacoast Bank. In communications with Key Bank | 2025-01-30
Fengate Fund IV - Most Favored Nation Side Letter | Fund Office / Legal / BOT |  | 2024-02-14
Obtain divorce decree from Broward County for Pension Applicant | Legal Counsel |  | 2024-02-11
Health & Welfare Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Plan Document | Legal | Bill to provide draft by upcoming meeting for review. Exec. Cmte mtg later to finalize | 2025-01-17
DOL Audit | DOL/ Legal | Bill received link from DOL recently to send their req'd additional documents. Follow Up from DOL on expenses/investments on Form 5500 | 2025-01-17
Contract with Sav Rx | Legal | In process with Sav Rx, not been the easiest company to deal with on contract | 2025-01-17
Stop Loss Claim Denial on Member | Legal / Stop Loss Broker | Bill to provide outline of next steps and potential cost of pursuit of claim appeal | 2025-01-17
Retirement Guide | Legal / BOT | Legal has edits, Kenny has edit. One guide or separate guides, Julie last pass with final. Provided to Julie | 2025-01-17
Meeting Minutes Review of 12/11/24; 1/29/25 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Family Statement Process - Ongoing Reinstatements | Fund Office |  | 2025-01-17
MAP informational mailing to members | Ulliance / BOT |  | 2025-01-17
Vision revised pricing for addition of safety glasses | Benefit Consultant | adding EyeMed to vendor selections. On 3/26/25 mttg agenda | 2025-01-17
Mental Health Program Pricing | Benefit Consultant | memo on 3/26/25 mtg agenda | 2025-01-17
Health Screening / Fair @ UH on 7/26/25 | Fund Office | Date to be moved to fall, Union to get calendar for available date. October 11, 2025 date for Health Screening | 2025-01-17
Sav Rx mailing to members regarding mail-order | Sav Rx / Benefit Consultant / Fund Office |  | 2025-01-17
A secondary mailing to members regarding Sav Rx | Fund Office |  | 2025-01-24
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase , Univest Bank & Trust, & Seacoast Bank. In communications with Key Bank | 2025-01-30
Service Corporation | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 8/2/24; 8/9/24; 8/23/24; 9/6/24; 9/13/23; 10/3/24; 10/11/24; 11/26/24; 12/11/24; 12/12/24; 12/20/24; 01/10/25; 01/24/25; 1/29/25; 2/7/25; 2/17/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 1/10/25; 1/24/25 | Fund Office | Bill & Jeff to develop a schedule to finalize minutes | 1/17/2025; 1/24/2025
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Payroll Audit Selection - Ongoing | Fund Office |  | 2025-01-17
PAR disclosure from Trinity & Protocol review | Legal | Bill will provide memo on PAR disclosures to Jeff & Lianet | 2025-01-17
Optimal Delinquencies - Lawsuit and Bond Claim | Legal | Lawsuit has been filed, service attempted unsuccessful. Send to SOS for service attempt. | 2025-01-17
Provide Collection Letters & Filings on Poole & Kent, Optimal & ForAir for Fund Office Files | Legal |  | 2025-01-17
Building Search & Acqusition - Ongoing | Exec Cmte / Legal / Fund Office / Actuary / Inv Consultant |  | 2025-01-17
Development of Construction / Transition / Moving Plan - Timeline | Legal / Fund Office |  | 2025-01-17
Participation Agreement for Affiliated Entities | Exec Cmte | Place on the February 25th Cmte Mtg agenda | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase , Univest Bank & Trust, & Seacoast Bank. In communications with Key Bank | 2025-01-30
Joint Apprenticeship & Training Committee Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 7/10/24; 7/11/24; 7/18/24; 8/7/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 9/12/24; 10/3/24; 11/21/24; 12/16/24; 1/8/25; 1/9/25; 2/3/25, 2/20/25 | Fund Office |  | 1/17/2025; 2/3/20205
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23;12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25; 2/28/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Curriculum Coordinator Posting / Recruitment Agency Contract | Legal |  | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase , Univest Bank & Trust, & Seacoast Bank. In communications with Key Bank | 2025-01-30
Missing Scholarship Loan Breach settlement payment from J. Marques | Legal |  | 2025-02-17
Langauage on Scholarship Loan Agreement Breach on iPads and Non-Returned Books | Legal |  | 2025-02-17

## Completed
Defined Contribution Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
1099R Payment & Report Reconciliation and Mailing / Filing of 1099R | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-15
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Defined Benefit Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Withdrawal calculation for Kaestle Enterprises | Actuary | Completed - On 1/29 BOT Mtg. | 2025-01-17 | 2025-01-29
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24; 11/26/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Recalculation of Working Retirees | Fund Office | Completed | 2025-01-17 | 2025-01-26
1099R Payment & Report Reconciliation and Mailing / Filing of 1099R | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-16
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Statements for PYE 12/31/24 | Fund Office | Sent to printer | 2025-01-17 | 2025-02-28
Develop & Send letter to contractors with the previous year EWL amount | Fund Office / Legal / BOT |  | 2025-01-24 | 2025-02-18
Health & Welfare Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24; | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Implementation of Retiree Subsidy Program Increase in months & maximum amount | Fund Office | Completed | 2025-01-17 | 2025-01-20
Implementation of Stop Loss Carrier Reporting and Payment | Stop Loss Broker / Fund Office | Completed | 2025-01-17 | 2025-01-19
W-2 Payment & Report Reconciliation and Mailing / Filing of W-2 | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-24
1095B Report Reconcilation and Mailing / Filing of 1095B | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-24
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Service Corporation | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Implementation of 100% Payroll Records Review | Fund Office / Payroll Auditor |  | 2025-01-17 | 2025-01-30
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Implementation of 100% Payroll Records Review | Fund Office / Payroll Auditor | Completed | 2025-01-17 | 2025-02-18
Joint Apprenticeship & Training Committee Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Recommendation of Cash Balances; Contribution Receivables; Capital & Operating Reserves | Acct'g / Fund Office | On Board 2/20/25 Meeting Agenda | 2025-01-17 | 2025-02-24